## Timeline
[Applicant Name] Project Timeline
Milestone Period
Program Milestone | Start (Month) | Duration (Months)
2026
|  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
Planning/Detailed Engineering | 1 | 1
Permitting/Make Ready | 1 | 1
Material & Equipment Procurement | 1 | 1
Network Deployment (Construction) | 1 | 1
Subscriber Activations | 1 | 1
Program Closeout Submission | 1 | 1
Directions:
To allow the ConnectMT Broadband Office to assess your proposed project timeline in a consistent and concise manner, it must be submitted via this standard program template.
For each program milestone, enter in the starting month (Cells C8 to C13) and milestone duration (Cells D8 to D13).
The project start (the beginning of Month 1) occurs January 1, 2026.
Milestone durations must be provided in units of months and are not to be tied to specific calendar dates.
Per program requirements, the project milestones may not extend beyond September 30, 2026.
The Program Closeout Submission milestone represents the month in which the applicant proposes to complete the project by submitting the required closeout materials.
The milestones must only encompass ARPA-funded deployment activities. Items such has ongoing subscriber activations (post program) and ongoing maintenance should not be included in the timeline.
Department of Administration
MONTANA ARPA Lightning Round